## API Inventory
API ID | Module | Method | Endpoint | Purpose / Kaam | When Hit / Kab Call Hogi | Primary Data Source | Cache Rule | Security Validation | Status | Priority
CTX-01 | MSS Context | GET | /ermobile/api/mss/v1/context | Active panel, profile, organisation and module permissions return karegi. | MSS/MSS_MO landing; profile switch; organisation switch; permission version change; expired context on app resume. | Mobile session DB + synced profile/permission data | Memory + SharedPreferences per profile/organisation; invalidate on version or selection change. | JWT, mobile session, profile ownership, organisation scope | Planned | P0
ORG-01 | Organisation | POST | /ermobile/api/mss/v1/organisations | MSS_MO parent ke allowed child organisations return karegi. Single MSS ke liye list call nahi hogi. | Login/context setup only for MSS_MO; organisation selector refresh. | R2 organisation hierarchy through mobile BFF | 30-second memory cache; persist active selection only. | MSS_MO profile and parent-child scope | Implemented | P0
FLT-01 | Filter Metadata | GET | /ermobile/api/mss/v1/approval-filters | Request types, approval levels/stages and branches provide karegi. | First approval page open; organisation/module change; cache version/TTL expiry; manual refresh. | R3 request catalog + R3 workflow + mobile synced branch DB | Memory + SharedPreferences key approvalFilters:{orgId}:{module}; stale-while-refresh. | JWT, session, active profile, organisation access | Implemented - version/TTL enhancement planned | P0
DSH-01 | Dashboard | GET | /ermobile/api/mss/v1/dashboard | Team dashboard counts and permission-aware quick actions return karegi. | Team dashboard enter; pull-to-refresh; profile/organisation switch; successful approval action. | R3 approval inbox aggregate + mobile permission context | Short memory cache 30-60 seconds, scoped by profile/org. | MSS/MSS_MO profile and module permissions | Planned | P0
APR-ATT-01 | Attendance Approval | GET | /ermobile/api/mss/v1/requisitions | Attendance pending/actioned approval list with summary and pagination. | Attendance card/quick action; filter/search/tab/page change; refresh. | R3 approval workflow inbox | No persistent list cache; optional current-page memory cache. | Attendance view permission + approver assignment | Planned | P0
APR-LEV-01 | Leave Approval | GET | /ermobile/api/mss/v1/requisitions | Leave pending/actioned approval list with summary and pagination. | Leave card/quick action; filter/search/tab/page change; refresh. | R3 approval workflow inbox + leave domain | No persistent list cache; optional current-page memory cache. | Leave view permission + approver assignment | Planned | P0
APR-OD-01 | OD Approval | GET | /ermobile/api/mss/v1/requisitions | On Duty pending/actioned approval list with summary and pagination. | OD card/quick action; filter/search/tab/page change; refresh. | R3 approval workflow inbox + OD domain | No persistent list cache; optional current-page memory cache. | OD view permission + approver assignment | Planned | P0
APR-WFH-01 | WFH Approval | GET | /ermobile/api/mss/v1/requisitions | Work From Home pending/actioned approval list. | WFH card/quick action; filter/search/tab/page change; refresh. | R3 approval workflow inbox | No persistent list cache. | WFH view permission + approver assignment | Planned | P0
APR-CMP-01 | Comp Off Approval | GET | /ermobile/api/mss/v1/requisitions | Comp Off pending/actioned approval list. | Comp Off card/quick action; filter/search/tab/page change; refresh. | R3 approval workflow inbox + leave ledger domain | No persistent list cache. | Comp Off view permission + approver assignment | Planned | P0
APR-DTL-01 | Approval Common | GET | /ermobile/api/mss/v1/requisitions/{requestId} | Selected requisition ki complete employee, request, stage, approver and action details. | Any requisition list item Review/Details click. | R3 workflow + relevant Attendance/Leave/OD/WFH/Comp Off domain | Memory only during detail session. | Request organisation/profile scope + current approver visibility | Planned | P0
APR-DEC-01 | Approval Common | POST | /ermobile/api/mss/v1/requisitions/{requestId}/decision | Attendance, Leave, OD, WFH and Comp Off approve/reject/send-back/forward action. | Detail page action confirmation. | R3 workflow decision service | Never cache; invalidate dashboard/list/detail after success. | Action permission, current pending level, optimistic locking/idempotency | Planned | P0
APR-HIS-01 | Approval Common | GET | /ermobile/api/mss/v1/requisitions/{requestId}/history | L1/L2/L3 approval timeline, approvers, remarks and timestamps. | Detail page History section open or detail payload lazy-load. | R3 workflow stages/audit | Memory cache until request action changes. | Request visibility permission | Planned | P1
APR-ATTCH-01 | Approval Common | GET | /ermobile/api/mss/v1/requisitions/{requestId}/attachments/{attachmentId} | Secure attachment preview/download without exposing internal file path. | User attachment click. | R3/R2 document storage through mobile BFF | HTTP cache headers where safe; no SharedPreferences payload. | Request visibility + attachment ownership | Planned | P1
APR-BULK-01 | Approval Common | POST | /ermobile/api/mss/v1/requisitions/bulk-decision | Selected requisitions ka bulk approve/reject. | Future bulk-selection confirmation only. | R3 workflow decision service | Never cache. | Every request independently validated; idempotency | Future | P2
TEAM-SUM-01 | My Team | GET | /ermobile/api/mss/v1/team/summary | Team strength, present, absent, leave, OD, joiner and exit summary. | People/My Team landing; refresh; profile/organisation change. | Mobile synced employee DB + R3 attendance summary | 30-60 second profile/org scoped cache. | Team hierarchy and profile scope | Planned | P1
TEAM-LST-01 | My Team | GET | /ermobile/api/mss/v1/team/employees | Reporting hierarchy ke allowed employees ki paginated list. | Employees/My Team screen; search/filter/page change. | Mobile synced employee/manager DB | Current-page memory cache only. | Profile permission + reporting hierarchy + organisation | Planned | P1
TEAM-DTL-01 | My Team | GET | /ermobile/api/mss/v1/team/employees/{employeeId} | Selected employee profile, reporting and employment details. | Employee list item click. | Mobile synced employee DB + R2 profile where required | Short memory cache. | Employee must be in allowed team scope | Planned | P1
TEAM-ATT-01 | My Team | GET | /ermobile/api/mss/v1/team/employees/{employeeId}/attendance-summary | Selected employee ka attendance summary. | Employee detail Attendance section open/date range change. | R3 attendance service | Date-range scoped short cache. | Employee team scope + attendance view permission | Planned | P2
IND-SUM-01 | Induction | GET | /ermobile/api/mss/v1/induction/summary | Induction/open onboarding counts. | Induction landing; refresh; profile/organisation change. | R2/R3 induction domain | 30-60 second scoped cache. | Induction view permission | Planned | P1
IND-LST-01 | Induction | GET | /ermobile/api/mss/v1/induction/employees | Induction employees/candidates paginated list. | Induction list open; filter/search/page change. | R2/R3 induction domain | Current-page memory cache only. | Induction view permission + organisation scope | Planned | P1
IND-DTL-01 | Induction | GET | /ermobile/api/mss/v1/induction/employees/{inductionId} | Candidate/employee induction details, documents and stages. | Induction list item click. | R2/R3 induction domain | Short memory cache. | Induction request visibility | Planned | P1
IND-ACT-01 | Induction | POST | /ermobile/api/mss/v1/induction/employees/{inductionId}/action | Induction approve/reject/complete stage action. | Induction detail action confirmation. | R2/R3 induction workflow | Never cache; invalidate induction summary/list/detail. | Induction action permission and current stage | Planned | P1
EXT-SUM-01 | Exit Employee | GET | /ermobile/api/mss/v1/exits/summary | Pending exit, notice, clearance and completed exit counts. | Exit landing; refresh; profile/organisation change. | R2/R3 exit domain | 30-60 second scoped cache. | Exit view permission | Planned | P1
EXT-LST-01 | Exit Employee | GET | /ermobile/api/mss/v1/exits/employees | Exit/resignation employees paginated list. | Exit list open; filter/search/page change. | R2/R3 exit domain | Current-page memory cache only. | Exit view permission + organisation/team scope | Planned | P1
EXT-DTL-01 | Exit Employee | GET | /ermobile/api/mss/v1/exits/employees/{exitRequestId} | Resignation, notice period, LWD, clearance, documents and history. | Exit employee list item click. | R2/R3 exit domain | Short memory cache. | Exit request visibility | Planned | P1
EXT-DEC-01 | Exit Employee | POST | /ermobile/api/mss/v1/exits/employees/{exitRequestId}/decision | Exit request approve/reject/send-back action. | Exit detail action confirmation. | R2/R3 exit workflow | Never cache; invalidate exit summary/list/detail. | Exit action permission and current level | Planned | P1

## Parameters
API ID | Parameter | Location | Type | Required | Allowed / Example | Description
ALL | Authorization | Header | String | Yes | Bearer <accessToken> | JWT access token.
ALL | X-Mobile-Session-Id | Header | String | Yes | mobile session UUID | Active mobile session validation.
ALL | X-Request-ID | Header | String | Recommended | UUID | Tracing; write APIs me idempotency correlation.
ORG-01 | activePanel | Body | String | Yes | MSS_MO | Only MSS_MO organisation listing allow hogi.
ORG-01 | profileId | Body | Long | Yes | 10 | Selected MSS_MO profile.
CTX-01 | organisationId | Query | Long | No | 15 | Absent ho to active session organisation use hogi.
CTX-01 | profileId | Query | Long | No | 10 | Absent ho to active profile use hoga.
FLT-01 | organisationId | Query | Long | Yes | 15 | Selected organisation ke branches/workflow stages.
FLT-01 | moduleCode | Query | String | No | TIME_ATTENDANCE / LEAVE / OD / WFH / COMP_OFF | Omit karne par all approval filter groups return kiye ja sakte hain.
DSH-01 | organisationId | Query | Long | Yes | 15 | Selected MSS/MSS_MO organisation.
DSH-01 | profileId | Query | Long | Yes | 10 | Counts selected profile permissions/assignments ke according.
APR-ATT-01 | module | Query | Enum | Yes | ATTENDANCE | Attendance approval list discriminator.
APR-LEV-01 | module | Query | Enum | Yes | LEAVE | Leave approval list discriminator.
APR-OD-01 | module | Query | Enum | Yes | OD | OD approval list discriminator.
APR-WFH-01 | module | Query | Enum | Yes | WFH | WFH approval list discriminator.
APR-CMP-01 | module | Query | Enum | Yes | COMP_OFF | Comp Off approval list discriminator.
APR-*-01 | organisationId | Query | Long | Yes | 15 | Selected organisation.
APR-*-01 | profileId | Query | Long | Yes | 10 | Selected profile.
APR-*-01 | tab | Query | Enum | No | PENDING / ACTIONED | Pending with me or actioned by me.
APR-*-01 | requestType | Query | String | No | REGULARIZATION | Request catalog filter.
APR-*-01 | stage | Query | Integer | No | 1 | Current approval level filter.
APR-*-01 | branchId | Query | Long | No | 25 | Synced branch filter.
APR-*-01 | search | Query | String | No | Ankur / EMP101 | Employee name, code or department search.
APR-*-01 | fromDate | Query | Date | No | 2026-08-01 | Applied/requested date range start.
APR-*-01 | toDate | Query | Date | No | 2026-08-31 | Applied/requested date range end.
LIST APIs | page | Query | Integer | No | 0 | Zero-based page number.
LIST APIs | size | Query | Integer | No | 20 | Page size; enforce backend maximum.
LIST APIs | sort | Query | String | No | STAGE_PRIORITY / NEWEST | Supported server-side sorting.
APR-DTL-01 | requestId | Path | Long/String | Yes | REQ-1001 | Unique approval request identifier.
APR-DTL-01 | module | Query | Enum | Yes | ATTENDANCE / LEAVE / OD / WFH / COMP_OFF | Correct domain details resolve karega.
APR-DEC-01 | decision | Body | Enum | Yes | APPROVE / REJECT / SEND_BACK / FORWARD | Approval action.
APR-DEC-01 | remarks | Body | String | Conditional | Approved | Reject/send-back par mandatory kar sakte hain.
APR-DEC-01 | version | Body | Long | Recommended | 3 | Optimistic locking; stale decision prevent karega.
APR-DEC-01 | clientActionId | Body | UUID | Yes | UUID | Duplicate approval submission prevent karega.
TEAM-LST-01 | branchId | Query | Long | No | 25 | Team branch filter.
TEAM-LST-01 | departmentId | Query | Long | No | 8 | Team department filter.
TEAM-LST-01 | status | Query | String | No | ACTIVE | Employment status filter.
TEAM-LST-01 | search | Query | String | No | EMP101 | Employee search.
TEAM-DTL-01 | employeeId | Path | Long | Yes | 10105 | Allowed team employee.
TEAM-ATT-01 | fromDate/toDate | Query | Date | No | 2026-08-01 / 2026-08-31 | Attendance summary range.
IND-LST-01 | stage | Query | String | No | DOCUMENT_VERIFICATION | Induction stage filter.
IND-LST-01 | status | Query | String | No | PENDING | Induction status filter.
IND-ACT-01 | action | Body | Enum | Yes | APPROVE / REJECT / COMPLETE | Induction workflow action.
IND-ACT-01 | remarks | Body | String | Conditional | Documents verified | Action remarks.
EXT-LST-01 | departmentId/branchId | Query | Long | No | 8 / 25 | Exit employee filters.
EXT-LST-01 | stage | Query | String | No | MANAGER_APPROVAL | Exit workflow stage.
EXT-LST-01 | status | Query | String | No | PENDING | Exit request status.
EXT-DEC-01 | decision | Body | Enum | Yes | APPROVE / REJECT / SEND_BACK | Exit decision.
EXT-DEC-01 | remarks | Body | String | Conditional | Approved | Decision remarks.

## Call Flow
Event / Screen | Step | API ID | API Call | Expected Behaviour
Fresh login with ESS permission | 1 | CTX-01 | No immediate MSS context call | ESS default active rahega; MSS API only profile select par.
Fresh login without ESS permission | 1 | CTX-01 | GET context after first profile becomes active | First MSS/MSS_MO profile and its organisation/permissions resolve honge.
ESS to MSS profile switch | 1 | CTX-01 | GET context | Old ESS context replace; only selected profile active.
MSS profile switch | 1 | CTX-01 | GET context | Profile permissions and active organisation reset/resolve.
MSS_MO profile selected | 2 | ORG-01 | POST organisations | Allowed child organisation selector populate.
Organisation changed | 1 | CTX-01 | GET context | New organisation permissions/context validate.
Organisation changed | 2 | FLT-01 | GET filters | New branches and workflow stages load; old org cache not reused.
Team dashboard open | 1 | DSH-01 | GET dashboard | Summary counts and quick actions load.
Attendance card click | 1 | APR-ATT-01 | GET requisitions?module=ATTENDANCE | Attendance list first page load.
Leave card click | 1 | APR-LEV-01 | GET requisitions?module=LEAVE | Leave list first page load.
OD card click | 1 | APR-OD-01 | GET requisitions?module=OD | OD list first page load.
WFH card click | 1 | APR-WFH-01 | GET requisitions?module=WFH | WFH list first page load.
Comp Off card click | 1 | APR-CMP-01 | GET requisitions?module=COMP_OFF | Comp Off list first page load.
First approval page in org/module | 1 | FLT-01 | GET filters only if cache missing/stale | Cached filters immediately show, background refresh when required.
Filter/search/tab/page changed | 1 | APR-*-01 | GET requisitions with query | Server-filtered paginated list and summary update.
Review clicked | 1 | APR-DTL-01 | GET requisition details | Complete domain and workflow details show.
History expanded | 1 | APR-HIS-01 | GET history if not included/cached | Approval timeline load.
Approve/reject confirmed | 1 | APR-DEC-01 | POST decision | Action validated and persisted once.
Approve/reject success | 2 | DSH-01 + APR-*-01 | Refresh dashboard and current list | Counts/order/list update; detail cache invalidate.
My Team tab open | 1 | TEAM-SUM-01 | GET team summary | Team KPIs load.
Employee list open | 1 | TEAM-LST-01 | GET team employees | Allowed hierarchy list load.
Employee clicked | 1 | TEAM-DTL-01 | GET employee details | Selected employee detail load.
Induction tab open | 1 | IND-SUM-01 + IND-LST-01 | GET summary and first page | Induction counts/list load.
Exit tab open | 1 | EXT-SUM-01 + EXT-LST-01 | GET summary and first page | Exit counts/list load.

## Approval Coverage
Approval Module | List API | Detail API | Decision API | History API | Attachment API | Dashboard Count | Filters | Coverage
Attendance | APR-ATT-01 module=ATTENDANCE | APR-DTL-01 module=ATTENDANCE | APR-DEC-01 module=ATTENDANCE | APR-HIS-01 | APR-ATTCH-01 | DSH-01 attendance | ATTENDANCE family + stage + branch | Included
Leave | APR-LEV-01 module=LEAVE | APR-DTL-01 module=LEAVE | APR-DEC-01 module=LEAVE | APR-HIS-01 | APR-ATTCH-01 | DSH-01 leave | LEAVE family + stage + branch | Included
On Duty (OD) | APR-OD-01 module=OD | APR-DTL-01 module=OD | APR-DEC-01 module=OD | APR-HIS-01 | APR-ATTCH-01 | DSH-01 od | OD family + stage + branch | Included
Work From Home | APR-WFH-01 module=WFH | APR-DTL-01 module=WFH | APR-DEC-01 module=WFH | APR-HIS-01 | APR-ATTCH-01 | DSH-01 wfh | WFH type + stage + branch | Included
Comp Off | APR-CMP-01 module=COMP_OFF | APR-DTL-01 module=COMP_OFF | APR-DEC-01 module=COMP_OFF | APR-HIS-01 | APR-ATTCH-01 | DSH-01 compOff | COMP_OFF type + stage + branch | Included